## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE |  | Config generator |  |  |  |  | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Implement framework
1.1 | Implement Event Receiver and Forwader | P.Hung |  |  | 0 | 100%
1.2 | Implement Share object | P.Hung |  |  | 0 | 100%
2 | Implement input handler
2.1 | Implement input file checker | P.Hung |  |  | 0 | 100%
2.2 | Implement input handler | P.Hung |  |  | 0 | 100%
2.2.1 | Implement excel format | P.Hung |  |  | 0 | 100%
2.2.2 | Implement csv format | Nghiem |  |  | 0 | 100%
2.3 | Implement data converter | P.Hung |  |  | 0 | 100%
2.4 | Implement input parameter share object | P.Hung |  |  | 0 | 100%
2.4.1 | Implement table ref obj | P.Hung |  |  | 0 | 100%
2.4.2 | Implement parameter obj | P.Hung |  |  | 0 | 100%
2.4.3 | Implement position obj | P.Hung |  |  | 0 | 100%
2.4.4 | Implement rule obj | P.Hung |  |  | 0 | 100%
3 | Implement data parser
3.1 | Implement table ref parser and obj | P.Hung |  |  | 0 | 100%
3.2 | Implement parameter parser and obj | Nghiem |  |  | 0 | 100%
3.3 | Implement position parser and obj | P.Hung |  |  | 0 | 100%
3.4 | Implement rule parser and obj | P.Hung |  |  | 0 | 0%
4 | Implement data integrator
4.1 | XML integrator | P.Hung |  |  | 0 | 0%
4.1.1 | Implement table ref and obj | P.Hung |  |  | 0 | 100%
4.1.2 | Implement parameter and obj | P.Hung |  |  | 0 | 100%
4.1.3 | Implement position and obj | P.Hung |  |  | 0 | 100%
4.1.4 | Implement rule and obj | P.Hung |  |  | 0 | 0%
4.2 | Source code integrator | Nghiem |  |  | 0 | 0%
4.2.1 | Implement normal table | Nghiem |  |  | 0 | 100%
4.2.2 | Implement special table | Nghiem |  |  | 0 | 100%
4.2.3 | Implement structure | Nghiem |  |  | 0 | 100%
4.2.4 | Implement acess function | Nghiem |  |  | 0 | 100%
4.2.5 | Implement delta table | Hoang |  |  | 0 | 100%
4.2.6 | Implement optimize design for table, structure and accessfunction | Hoang |  |  | 0 | 100%
4.2.6 | Implement interface mask | Hoang |  |  | 0 | 0%
5 | Implement report handler
5.1 | XML | P.Hung |  |  | 0 | 0%
5.1.1 | Implement report template checker | P.Hung |  |  | 0 | 100%
5.1.2 | Implement table ref | P.Hung |  |  | 0 | 100%
5.1.3 | Implement parameter | P.Hung |  |  | 0 | 100%
5.1.4 | Implement position | P.Hung |  |  | 0 | 100%
5.1.5 | Implement rule | P.Hung |  |  | 0 | 0%
5.2 | Source code | Nghiem |  |  | 0 | 0%
5.2.1 | Implement report template checker | P.Hung |  |  | 0 | 100%
5.2.2 | Implement broadcast config to other report handler | P.Hung |  |  | 0 | 100%
5.2.3 | Implement normal table | Nghiem |  |  | 0 | 100%
5.2.4 | implement special table | Nghiem |  |  | 0 | 100%
5.2.5 | Implement structure | Nghiem |  |  | 0 | 100%
5.2.6 | Implement access function | Nghiem |  |  | 0 | 100%
5.2.7 | Implement delta table | Hoang |  |  | 0 | 100%
5.2.8 | Implement optimize design for table, structure and accessfunction | Hoang |  |  | 0 | 100%
6 | Configuration
6.1 | Implement interface list | Hoang |  |  | 0 | 100%
6.2 | Implement exception item | Hoang |  |  | 0 | 100%
6.3 | Implement name space | Hoang |  |  | 0 | 0%
6.4 | Implement .cpp or .h file | Hoang |  |  | 0 | 0%
6.5 | Implement byte optimize | Hoang |  |  | 0 | 100%
6.6 |  |  |  |  | 0 | 0%
x | Misc
x.1 | Implement console | P.Hung |  |  | 0 | 0%
x.2 | XML bug fixing | P.Hung |  |  |  | 0%
x.3 | Code bug fixing | Hoang |  |  |  | 0%
x.4 | [5 empty] | 0%